**FEBRUARY REPORT ON LATAM TOUR 2015 – Andrea Villar**

**CHAPTERS**

**PERU-** Lima: The UTP  University Directory  change and they  did not respect the signed letter offering rooms for the conferences. They are trying to get a sponsors to provide them a room. If they don’t get  one Fabio is going to  contact the OAS who volunteered to participate not with money but with inputs directly, to provide a venue in the city of Lima. We do not have list of speakers and trainers yet.

**CHILE-** Santiago: We have not had any communication with the leader, we have sent several e mail and copy to his personal address. He has not attended the meetings we had with the leaders by Go to Meeting fortnightly.

**COLOMBIA-** Bucaramanga: Just make a day of conferences. There will be broadcast via streaming for persons located outside the city.

**URUGUAY -** Montevideo: The do not have list of speakers claiming they are holiday periods in the region and have not been able to advance. They requested an extension and we commented them that we did not allow it with other chapters. We continue communicating with them daily expecting an answer.

**BOLIVIA-** Santa Cruz :  It is confirmed and already have the full list of speakers (16) and we are in contact with the speakers that would fund OWASP to coordinate their travel.

**COSTA RICA –** San José:  In response to the venue of the training will be a governmental organization (Ministry of Science and Technology of Costa Rica). However, the training cannot have a cost per their policy.

The chapter leader thought that a sponsor would pay for 30 trainings and no charge to those who attended. The situation is that once they have contact with this company will put them in communication with Kelly to perform a special deal for their participation.

**GUATEMALA-** Guatemala: We have not had any communication with the leader, we have sent several email and copy to his personal address. He has not attended the meetings we had with the leaders by Go to Meeting fortnightly.

**ARGENTINA –** Buenos Aires: We have not had any communication with the leader, we have sent several email and copy to his personal address. He has not attended the meetings we had with the leaders by Go to Meeting fortnightly.

**ARGENTINA –** Patagonia: The chapter has completed the list of speaker and we are in communication with speakers that OWASP must fund to manage their tickets.

They are going to make up T shirt with OWASP logo for sale at the venue and profits remain in the chapter. We request them to send us the design for approval.

**VENEZUELA –** Caracas: We have a difficult situation with the chapter on Venezuela for the control of change that exists in the country, they have problems difficulty to collect sponsorship in US dollars.

In previous years they work just with one level of sponsorship and companies could covered the event needs (coffee breaks, refreshments, etc). They can't receive money because don't have legal status to do it and if OWASP receive the payment directly confronted with the difficulty of change control.

A peculiarity of the last event was that because of this difficulty with the sponsorship and complexity to get tickets with good price tor Venezuela performed a local event with national speakers, international speakers was presented  by video conference.  This year they are going to do the same.

**ECUADOR-** Student Chapter :  They have already booked the room for two days, but if we ask to do it in one day, they  do not have problem.  Fabio think if Ramiro Pulgar from Quito don’t support them not allow completion of this chapter

**SPONSORS**

**Platinum Sponsors**

AKAMAI TECHNOLOGIES   -  they are going to be at the stops of Colombia, Chile, Costa Rica and Perú.

**Community Supporters**

SEGUINFO

[DRAGONJAR.ORG](http://dragonjar.org/)

**Supporting Partners**

MundoHackerTV -

**Andrea Villar**

**Global Conference Manager**

**OWASP Foundation**