## Detailed
Focus Areas: |  |  |  |  | DETAILED CONFERENCE CHECKLIST
Internal Communication and Planning
External Communication & Community Outreach
Event Venue & Logistics
Event Content (Speakers & Trainers)
Event Sponsors
Event Finance
Bold- Deadline, Required Action Item
| Item No. | Area | WHEN actions/tasks should be completed (recommended deadlines) | WHAT actions/tasks need to be done | HOW to complete - guidelines, related documents & templates | WHO do I work with on this or contact if I have questions?
| 101 | Internal Comm & Planning | 12 mos. before event (as early as possible in planning process) | Put together a local volunteer team & select chair
| 102 | Internal Comm & Planning | 12 mos. before event (as early as possible in planning process) | Enter event into OEMS & get approval from GCC | https://ocms.owasp.org/
| 103 | Venue & Logistics | 12 mos. before event (as early as possible in planning process) | Start looking at possible venues (including dates of availability and pricing)
| 104 | Internal Comm & Planning | 12 mos. before event (as early as possible in planning process) | Work with OWASP staff to determine needs for event website, graphics, marketing, and PR
| 105 | Internal Comm & Planning | 12 mos. before event (as early as possible in planning process) | Draft event communications plan & delgate responsibilities
| 106 | Sponsors | 12 mos. before event (as early as possible in planning process) | Put together event sponsorship pricing & packages
| 107 | Finance | 12 mos. before event (as early as possible in planning process) | Submit event budget with costs & income to GCC and Staff for review
| 108 | Finance | 12 mos. before event (as early as possible in planning process) | Discuss with OWASP Staff any possible issues with making and receiving payments in local currency
| 109 | Internal Comm & Planning | Ongoing - starting 9 or 10 mos. before event | Hold periodic (weekly or bi-monthly) volunteer planning meetings to discuss logistics, outreach, content (speakers/trainers), and other planning needs.
| 110 | Internal Comm & Planning | Ongoing - starting 9 or 10 mos. before event | Member of the local planning team (chair or other) attend monthly Global Conference Committee call, providing status updates on logistics, content and budget. Includes post event wrap-up.
| 111 | Internal Comm & Planning | Ongoing - starting 9 or 10 mos. before event | Local planning chair(s) hold weekly or bi-monthly call with SB (OWASP Staff) to communicate about conference updates and coordinate action items before and after event.
| 112 | External Comm & Outreach | Start drafting 9-10 mos. before event, going "live" by 9 mo. before event | Launch event website
| 113 | Venue & Logistics | 9-10 mos. before event | Negotiate venue: time, rooms, food, min spend
| 114 | External Comm & Outreach | 9-10 mos. before event | Set up (tranfer) social media accounts
| 115 | External Comm & Outreach | 9-10 mos. before event | Contact other infosec groups (ISACA, ISSA, ISC2) about co-marketing agreements
| 116 | External Comm & Outreach | 9-10 mos. before event | Contact educational institutions, government & industry for support/patronage
| 117 | External Comm & Outreach | Ongoing - starting 9 or 10 mos. before event | Implement event communications plan: including press releases, announcements regarding speakers, trainers, and sponsors. Coordinate social media postings and updates to event website
| 118 | Sponsors | Ongoing - starting 9 or 10 mos. before event (sponsors should be finalized by 1 mo. before event) | OBTAIN SPONSORSHIP: Work with OWASP Staff to solicit event sponsorships & establish central place to track communication with sponsors. As sponsors commit, collect graphics for website and other conference materials. Update sponsorship document based on availability (ie. number of gold sponsorships remaining)
| 119 | Finance | Ongoing - starting 9 or 10 mos. before event | Provide monthly budget updates to OWASP Staff and GCC, per budgeting guidelines. Should include itemized projections/actuals on expenses and income
| 120 | Finance | Ongoing - starting 9 or 10 mos. before event | Send all invoices, receipts for reimbursement, payment schedules, and other financial paperwork to Alison for processing
| 121 | Content | 9 mos. before event | Solicit Keynote Speakers
| 122 | Venue & Logistics | 9 mos. before event | DEADLINE: Send venue contract to OWASP Staff for signature
| 123 | Content | 6 mos. before event | Finalize Keynote Speakers
| 124 | Venue & Logistics | 6 mos. before event | Check-in with venue to confirm details
| 125 | Content | 6 mos. before event | Launch Call for Trainers - CFT
| 126 | Content | 6 mos. before event | Launch Call for Speakers / Papers- CFP
| 127 | Content | 6 mos. before event | Launch Call for talks (projects) for OWASP Track
| 128 | External Comm & Outreach | 4-6 mos. before event (coordinate as part of communications plan) | Announce Keynote speakers
| 129 | Venue & Logistics | 4-6 mos. before event (or earlier) | Find hotel room block(s)
| 130 | Content | 4-6 mos. before event (or earlier) | Start planning other conference events : CTF, committee workshops, OSS, University Challenge, social events, etc
| 131 | External Comm & Outreach | 3-4 mos. before event, DEADLINE 90 days before event | DEADLINE: Launch Event Registration Site | cvent
| 132 | Venue & Logistics | 3-4 mos. before event (or earlier) | Find vendors (if needed) for AV, internet, merch, equip, translation, and social events
| 133 | Content | 3-4 mos. before event | Select (at least 1st round) of speakers & trainers. Notify speakers & trainers of status, send & collect paperwork
| 134 | Internal Comm & Planning | 2 mos/60 days before event | Call for on-site volunteers - confirm availability of volunteers who have already committeed, solicit more volunteers if needed
| 135 | Content | DEADLINE: 2 mos/60 days before event | DEADLINE CFP/CFT - make final selections, notify speakers & trainers of whether accepted or not, send and collect paperwork
| 136 | Venue & Logistics | 6 wks before event | Order event-specific merch (tshirts, bags, pens, etc)
| 137 | Venue & Logistics | 6 wks before event | Review hotel room block: compare to VIP list, determine availability
| 138 | Content | 6 wks before event | Ensure all speakers confirmed & send details
| 139 | Content | 6 wks before event | Send weekly reports to trainers with number of students registered
| 140 | Sponsors | 6 wks before event | Send out sponsor info kit - shipping address & event info
| 141 | Venue & Logistics | 4 wks before event | Coordinate shipment of standard OWASP merch, banners, & equiment
| 142 | Venue & Logistics | 4 wks before event | Confirm AV & network needs w/ venue (or provider)
| 143 | Content | 3 wks before event | DEADLINE: Finalize conference schedule and send to printer
| 144 | Sponsors | 3-4 wks before event | Confirm details and registration with sponsors
| 145 | Venue & Logistics | 1-2 wks before event | Provide final food counts & special dietary needs to venue
| 146 | Venue & Logistics | 1-2 wks before event | Order signage & schedules
| 147 | Venue & Logistics | 1-2 wks before event | Merch, supplies, & equipment shipped
| 148 | Venue & Logistics | 1-2 wks before event | Conference programs shipped
| 149 | Sponsors | 1-2 wks before event | Sponsors to ship inserts/ brochures for attendee bags, booth supplies
| 150 | Venue & Logistics | 1-2 days before event | Confirm details with venue & onsite walk-through
| 151 | Venue & Logistics | 1-2 days before event | Print name badges & Set up registration area
| 152 | Internal Comm & Planning | 1-2 days before event | Meet with volunteers to go through timeline & responsibilities
| 153 | Venue & Logistics | 1-2 days before event | Attendee bags - stuff w/ sponsor materials, program, etc
| 154 | Content | 1-2 days before event and during event as needed | Collect and review speaker slides
| 155 | Internal Comm & Planning | During Event | Monitor daily activities: ensure trainers & speakers show up & know where to go, AV /network is up & running, food and coffee breaks are on time
| 156 | External Comm & Outreach | During Event | Collect training & talk feedback
| 157 | Internal Comm & Planning | During Event | Monitor video collection of conference talks, dump SD cards as needed
| 158 | Internal Comm & Planning | During Event | Ensure registration & info booth is staffed at all times
| 159 | Internal Comm & Planning | During or after Event | Hold thank you event for volunteers/staff
| 160 | Sponsors | Before, during, and after Event | Circulate vendor/booth area for questions before (set up), during, and after (tear down) event. Provide return shipment instructions.
| 161 | Content | To be completed by 1 week after event | Collect remaining speaker slides
| 162 | Venue & Logistics | To be completed by 1 week after event | Mail event video for production
| 163 | External Comm & Outreach | To be completed by 1 week after event | Send post-event survey to attendees
| 164 | Finance | To be completed by 1 week after event | Collect invoices and sign-in sheets from trainers
| 165 | Sponsors | As soon as possible after event, no later than 1 month after event | Send thank you notes to sponsors and solicit event feedback
| 166 | Finance | As soon as possible after event, completed by 2 months after event | Work with OWASP Staff to finalize all incoming & outgoing payments
| 167 | Content | As soon as possible after event, completed by 3 months after event | Post conference slides video to website & email attendees to let them know that video and slides are available
| 168 | External Comm & Outreach | 1 month after event | Send feedback to trainers & speakers
| 169 | External Comm & Outreach | As soon as possible after event, no later than 1 month after event | Send thank you notes to keynotes & speakers
| 170 | Finance | As soon as possible after event, no later than 1 month after event | Finalize payment to trainers
| 171 | Internal Comm & Planning | To be completed by 3 months after event | Transition social media accounts to next year's team
| 172 | Internal Comm & Planning | To be completed by 3 months after event | Compile conference lessons learned & notes for next year's team
| 173 | Sponsors | To be completed by 3 months after event | Share sponsor feedback with next year's event team

## Overview
OWASP GLOBAL APPSEC - CONFERENCE TIMELINE
PRE-CONFERENCE | [10 empty] | DURING CONFERENCE | POST-CONFERENCE
START 12 MONTHS | 9-10 MONTHS | 9 MONTHS | 6 MONTHS | 4 - 6 MONTHS | 3-4 MONTHS | 2 MONTHS | 6 WEEKS | 3-4 WEEKS | 1 -2 WEEKS | 1 - 2 DAYS |  | 1 WEEK | 1 MONTH | 2-3 MONTHS
Put together a local volunteer team & select chair (101) | Hold periodic (weekly or bi-monthly) volunteer planning meetings to discuss logistics, outreach, content (speakers/trainers), and other planning needs (109)
Member of the local planning team (chair or other) attend monthly Global Conference Committee call, providing status updates on logistics, content and budget. Includes post event wrap-up (110)
Local planning chair(s) hold weekly or bi-monthly call with SB (OWASP Staff) to communicate about conference updates and coordinate action items before and after event. (111)
Enter event into OEMS & get approval from GCC (102) | Launch event website (112) | Solicit Keynote Speakers (121) | Finalize Keynote Speakers (123) | Announce Keynote speakers (128) | DEADLINE: Launch Event Registration (131) | Call for on-site volunteers (134) | Order event-specific merch (tshirts, bags, pens, etc) (136) | Coordinate shipment of standard OWASP merch, banners, & equiment (141) | Provide final food counts & special dietary needs to venue (145) | Confirm details with venue & onsite walk-through (150) | Collect and review speaker slides (154) | Collect remaining speaker slides (161) | Post conference slides video to website & email attendees to let them know that video and slides are available (167)
Monitor daily activities: ensure trainers & speakers show up & know where to go, AV /network is up & running, food and coffee breaks are on time (155)
Start looking at possible venues (including dates of availability and pricing) (103) | Negotiate venue: time, rooms, food, min spend (113) | DEADLINE: Send venue contract to OWASP Staff for signature (122) | Check-in with venue to confirm details (124) | Find hotel room block(s) (129) | Find vendors (if needed) for AV, internet, merch, equip, translation, and social events (132) | [6 empty] | Mail event video for production (162)
Send feedback to trainers & speakers (168)
[7 empty] | Review hotel room block: compare to VIP list, determine availability (137) |  | Order signage & schedules (146) | Print name badges & Set up registration area (151) |  |  |  | Compile conference lessons learned & notes for next year's team (171)
|  |  | Launch Call for Trainers - CFT (125) | Start planning other conference events : CTF, committee workshops, OSS, University Challenge, social events, etc (130) | Select (at least 1st round) of speakers & trainers. Notify speakers & trainers of status, send & collect paperwork (133) | DEADLINE CFP/CFT - make final selections, notify speakers & trainers of whether accepted or not, send and collect paperwork (135) |  | Confirm AV & network needs w/ venue (or provider) (142) |  |  |  | Send post-event survey to attendees (163)
Collect training & talk feedback (156)
| Set up (tranfer) social media accounts (114) | [7 empty] | Merch, supplies, & equipment shipped (147) |  |  |  | Send thank you notes to keynotes & speakers (169)
|  |  | Launch Call for Speakers / Papers CFP (126) | [6 empty] | Meet with volunteers to go through timeline & responsibilities (152) | Monitor video collection of conference talks, dump SD cards as needed (157)
Work with OWASP staff to determine needs for event website, graphics, marketing, and PR (104) | Contact other infosec groups (ISACA, ISSA, ISC2) about co-marketing agreements (115) | [10 empty] | Collect invoices and sign-in sheets from trainers (164)
[7 empty] | Ensure all speakers confirmed & send details (138) | DEADLINE: Finalize conference schedule and send to printer (143) | [5 empty] | Transition social media accounts to next year's team (172)
[9 empty] | Conference programs shipped (148) |  | Ensure registration & info booth is staffed at all times (158) |  | Finalize payment to trainers (170)
| Contact educational institutions, government & industry for support/patronage (116) |  | Launch Call for talks for OWASP Track (127)
Draft event communications plan & delgate responsibilities (105) | [10 empty] | Hold thank you event for volunteers/staff (159)
Send weekly reports to trainers with reg #s (139)
Implement event communications plan: including press releases, announcements regarding speakers, trainers, and sponsors. Coordinate social media postings and updates to event website (117)
Put together event sponsorship pricing & packages (106) | OBTAIN SPONSORSHIP: Work with OWASP Staff to solicit event sponsorships & establish central place to track communication with sponsors. As sponsors commit, collect graphics for website and other conference materials. Update sponsorship document based on availability (ie. number of gold sponsorships remaining) (118) | [5 empty] | Send out sponsor info kit - shipping address & event info (140) | Confirm details and registration with sponsors (144) | Sponsors to ship inserts/ brochures for attendee bags, booth supplies (149) | Attendee bags - stuff w/ sponsor materials, program, etc (153) | Circulate vendor/booth area for questions before (set up), during, and after (tear down) event. Provide return shipment instructions. (160) | Send thank you notes to sponsors and solicit event feedback (165) |  | Share sponsor feedback with next year's event team (173)
Submit event budget with costs & income to GCC and Staff for review (107)
Provide monthly budget updates to OWASP Staff and GCC, per budgeting guidelines. Should include itemized projections/actuals on expenses and income (119)
Discuss with OWASP Staff any possible issues with making and receiving payments in local currency (108) | Send all invoices, receipts for reimbursement, payment schedules, and other financial paperwork to Alison for processing (120) | [10 empty] | Work with OWASP Staff to finalize all incoming & outgoing payments (166)
Focus Areas
Internal Communication and Planning
External Communication & Community Outreach
Venue & Logisitics
Event Content (Speakers, Trainers, etc.)
Event Sponsors
Event Finances
[7 empty] | BOLD | Deadline - Required action items